## Tasks
ID | Phase | Task | Subtask | Details / Description | Priority | Est. Hours | Status | Dependencies
T-001 | 1. Project Setup & Environment | Initialize Tauri + React project | Scaffold project with Tauri CLI | Run `create-tauri-app` with React + Vite template; verify native window launches on Windows. | High | 3 | Completed
T-002 | 1. Project Setup & Environment | Initialize Tauri + React project | Configure Tailwind CSS | Install Tailwind, set up config and base styles, confirm hot-reload works inside the Tauri window. | High | 2 | Completed
T-003 | 1. Project Setup & Environment | Initialize Tauri + React project | Set up project folder structure | Create feature-based folder structure: /features (orders, menu, payments), /components, /lib, /store. | Medium | 2 | Completed
T-004 | 1. Project Setup & Environment | Version control & tooling | Set up Git repository and branching strategy | Initialize repo, set up main/dev branches, add .gitignore for Tauri/Rust/Node artifacts. | Medium | 1 | Completed
T-005 | 1. Project Setup & Environment | Version control & tooling | Configure ESLint, Prettier, and commit hooks | Add lint/format config consistent with existing MERN projects; add pre-commit hook via husky. | Low | 2 | Completed
T-006 | 1. Project Setup & Environment | Backend project setup | Initialize Node.js + Express project | Scaffold Express app with folder structure for routes/controllers/services/models. | High | 2 | Completed
T-007 | 1. Project Setup & Environment | Backend project setup | Set up PostgreSQL and Prisma | Install PostgreSQL locally, configure Prisma, run first migration to confirm connectivity. | High | 3 | Completed
T-008 | 1. Project Setup & Environment | Local database setup | Integrate SQLite via tauri-plugin-sql | Add SQLite plugin to Tauri app, confirm read/write from React front end through Rust bridge. | High | 3 | Completed
T-009 | 2. Database & Schema Design | Design local SQLite schema | Define core tables (orders, order_items, payments) | Design tables mirroring SRS data model with UUID primary keys, synced/created_locally_at fields. | High | 5 | Not Started
T-010 | 2. Database & Schema Design | Design local SQLite schema | Define menu & inventory tables | menu_categories, menu_items, item_variants, modifiers, ingredients, recipe_links tables. | High | 4 | Not Started
T-011 | 2. Database & Schema Design | Design local SQLite schema | Define users & audit tables | users, roles, audit_log tables with hashed PIN storage. | High | 2 | Not Started
T-012 | 2. Database & Schema Design | Design backend PostgreSQL schema | Mirror local schema on server with sync metadata | Add synced_at, server_received_at, conflict_flag columns for reconciliation logic. | High | 4 | Not Started
T-013 | 2. Database & Schema Design | Design backend PostgreSQL schema | Define reporting-oriented views/indexes | Add indexes on order date, staff id, payment method for fast report queries. | Medium | 3 | Not Started
T-014 | 2. Database & Schema Design | Seed & migration scripts | Write seed data for menu and test users | Create seed script with sample categories, items, modifiers, and one Admin/Cashier/Waiter user each. | Medium | 2 | Not Started
T-015 | 3. Authentication & User Management | PIN-based login | Build login screen (PIN pad UI) | Numeric keypad UI matching touchscreen usability requirements (NFR-4.1). | High | 3 | Not Started
T-016 | 3. Authentication & User Management | PIN-based login | Implement local PIN verification (offline-capable) | Hash PIN with bcrypt, verify against locally cached user table (FR-1.6). | High | 4 | Not Started
T-017 | 3. Authentication & User Management | PIN-based login | Implement quick user-switch without full logout | Add lightweight session swap so a new PIN entry switches active user context (FR-1.5). | Medium | 3 | Not Started
T-018 | 3. Authentication & User Management | Role-based access control | Define role permission matrix in code | Central permissions config mapping Admin/Manager/Cashier/Waiter/Kitchen to allowed actions. | High | 3 | Not Started
T-019 | 3. Authentication & User Management | Role-based access control | Guard routes/components by role | Wrap protected UI routes and buttons (e.g. void, discount) with permission checks. | High | 3 | Not Started
T-020 | 3. Authentication & User Management | User management screens | Admin CRUD screen for staff accounts | Create/edit/deactivate/delete users, assign roles (FR-1.3). | Medium | 4 | Not Started
T-021 | 3. Authentication & User Management | Audit logging | Log user + timestamp on sensitive actions | Write audit_log entries for voids, discounts, price overrides, and login events (FR-1.4, NFR-3.3). | High | 3 | Not Started
T-022 | 4. Menu Management | Category management | CRUD for menu categories | Admin screen to create/edit/delete/reorder categories (FR-2.1). | High | 3 | Not Started
T-023 | 4. Menu Management | Menu item management | CRUD for menu items with pricing and tax rate | Form with name, description, price, tax rate, category, image upload (FR-2.2). | High | 5 | Not Started
T-024 | 4. Menu Management | Menu item management | Variant support (size/type pricing) | Add variant sub-form allowing multiple priced options per item (FR-2.3). | High | 4 | Not Started
T-025 | 4. Menu Management | Menu item management | Modifier / add-on support | Attach reusable modifiers (extra cheese, spice level) with price deltas to items (FR-2.4). | Medium | 4 | Not Started
T-026 | 4. Menu Management | Menu item management | Combo/bundle item builder | UI to compose a combo from multiple items at a bundled price (FR-2.5). | Medium | 5 | Not Started
T-027 | 4. Menu Management | Availability control | 86'd / unavailable item toggle | One-tap toggle to hide item from ordering screen in real time without deleting it (FR-2.6). | High | 2 | Not Started
T-028 | 4. Menu Management | Availability control | Time-based menu availability windows | Config for start/end time per item or category (e.g. breakfast menu) (FR-2.7). | Low | 3 | Not Started
T-029 | 5. Order Management | Order creation flow | Order type selection (Dine-in/Takeaway/Delivery) | Entry screen branching into table selection or customer info form (FR-3.1, FR-3.2). | High | 3 | Not Started
T-030 | 5. Order Management | Order creation flow | Cart/line item builder | Add/edit/remove items with quantity, variant, modifiers, and notes (FR-3.3, FR-3.4). | High | 6 | Not Started
T-031 | 5. Order Management | Order creation flow | Client-side UUID generation for new orders | Generate UUID at order creation so offline orders remain unique after sync (FR-3.10). | High | 2 | Not Started
T-032 | 5. Order Management | Kitchen routing | Send order / new items to kitchen | Action to push new or modified line items as a kitchen ticket (FR-3.5). | High | 3 | Not Started
T-033 | 5. Order Management | Order lifecycle | Implement order status state machine | Enforce Open -> Sent to Kitchen -> In Prep -> Ready -> Served -> Paid -> Closed transitions (FR-3.6). | High | 4 | Not Started
T-034 | 5. Order Management | Order corrections | Void order/item with approval workflow | Manager/Admin PIN confirmation and reason code capture on void (FR-3.7). | High | 3 | Not Started
T-035 | 5. Order Management | Order corrections | Reopen closed order within time window | Allow reopening for corrections within configurable window, Admin/Manager only (FR-3.9). | Medium | 3 | Not Started
T-036 | 5. Order Management | Table billing operations | Merge tables / split bill | UI to combine two open table orders or split one order into multiple bills (FR-3.8). | Medium | 5 | Not Started
T-037 | 6. Table & Floor Management | Floor plan builder | Admin floor plan layout editor | Drag-and-drop table placement, numbering, capacity config (FR-4.2). | Medium | 5 | Not Started
T-038 | 6. Table & Floor Management | Floor plan builder | Live floor plan view with table status | Visual grid showing Free/Occupied/Reserved/Needs Cleaning states (FR-4.1). | High | 4 | Not Started
T-039 | 6. Table & Floor Management | Table assignment | Assign waiter to table/section | Manager screen to assign staff to sections for a shift (FR-4.3). | Low | 2 | Not Started
T-040 | 6. Table & Floor Management | Automatic status updates | Auto-update table status on order events | Hook table status changes to order lifecycle events (e.g. auto 'Needs Cleaning' on close) (FR-4.4). | Medium | 3 | Not Started
T-041 | 7. Kitchen Display System (KDS) | KDS core screen | Build real-time ticket queue view | Kitchen-facing screen listing tickets in time order via Socket.IO (FR-5.1). | High | 5 | Not Started
T-042 | 7. Kitchen Display System (KDS) | KDS core screen | Item/ticket status controls (In Progress/Ready) | Buttons for kitchen staff to update prep status per item or full ticket (FR-5.2). | High | 3 | Not Started
T-043 | 7. Kitchen Display System (KDS) | KDS alerts | Prep-time threshold visual flagging | Highlight tickets exceeding configurable prep time (FR-5.3). | Medium | 2 | Not Started
T-044 | 7. Kitchen Display System (KDS) | KDS alerts | Ready notification back to waiter/cashier | Push notification/badge to POS terminal when kitchen marks ticket Ready (FR-5.4). | Medium | 3 | Not Started
T-045 | 7. Kitchen Display System (KDS) | KDS offline behavior | LAN-only fallback mode for KDS | Ensure KDS keeps functioning via local network/server when internet is down (FR-5.5). | High | 4 | Not Started
T-046 | 8. Payment Processing | Payment methods | Cash payment flow with change calculation | Cash tendered input, automatic change-due calculation (FR-6.1, FR-6.6). | High | 3 | Not Started
T-047 | 8. Payment Processing | Payment methods | Card and mobile wallet payment flow | UI for card/JazzCash/Easypaisa entry, with offline 'pending verification' state (FR-6.1, FR-6.7). | High | 4 | Not Started
T-048 | 8. Payment Processing | Bill splitting | Split bill across methods or customers | Equal split and custom-amount split UI across multiple payments per order (FR-6.2). | Medium | 5 | Not Started
T-049 | 8. Payment Processing | Tax & discounts | Automatic tax calculation engine | Apply configured tax rules per item/category on order totals (FR-6.3). | High | 3 | Not Started
T-050 | 8. Payment Processing | Tax & discounts | Discount application with approval threshold | Percentage/fixed discount entry with Manager/Admin approval above configurable threshold (FR-6.4). | Medium | 3 | Not Started
T-051 | 8. Payment Processing | Tips | Tip entry and allocation | Add tip field to payment screen, allocate to staff if applicable (FR-6.5). | Low | 2 | Not Started
T-052 | 9. Inventory Management | Recipe linking | Link menu items to ingredient quantities | Bill-of-materials style form linking each menu item to ingredient usage (FR-7.1). | Medium | 4 | Not Started
T-053 | 9. Inventory Management | Stock deduction | Auto-deduct stock on order finalization | Deduct linked ingredient quantities when an order is paid/closed (FR-7.2). | High | 4 | Not Started
T-054 | 9. Inventory Management | Stock alerts | Low-stock threshold alerts | Notify Admin/Manager when ingredient stock crosses reorder threshold (FR-7.3). | Medium | 2 | Not Started
T-055 | 9. Inventory Management | Stock alerts | Auto-disable menu item at zero stock | Automatically mark item unavailable when linked ingredient hits zero (FR-7.5). | Medium | 2 | Not Started
T-056 | 9. Inventory Management | Manual adjustments | Manual stock adjustment screen with audit log | Screen for receiving stock, recording wastage/corrections, logged to audit trail (FR-7.4). | Low | 3 | Not Started
T-057 | 10. Receipt & Printing | Printer integration | ESC/POS printer driver integration (Rust side) | Integrate escpos crate in Tauri Rust layer for USB/LAN thermal printers. | High | 5 | Not Started
T-058 | 10. Receipt & Printing | Printer integration | Print customer receipt on payment completion | Trigger receipt print with itemized details, tax, discount, total, payment method (FR-8.1, FR-8.5). | High | 3 | Not Started
T-059 | 10. Receipt & Printing | Printer integration | Print kitchen tickets to kitchen printer | Optional printed kitchen ticket alongside/instead of KDS display (FR-8.2). | Medium | 3 | Not Started
T-060 | 10. Receipt & Printing | Print reliability | Print job queue with retry on failure | Queue and retry logic so a disconnected printer never blocks order completion (FR-8.3). | High | 3 | Not Started
T-061 | 10. Receipt & Printing | Print reliability | Reprint receipt for closed order | Lookup and reprint historical receipts (FR-8.4). | Low | 2 | Not Started
T-062 | 11. Offline Operation & Sync Engine | Local-first data flow | Write-to-SQLite-first architecture | Ensure every transactional write hits local SQLite before any network call is attempted (FR-9.1, FR-9.2). | High | 5 | Not Started
T-063 | 11. Offline Operation & Sync Engine | Sync engine | Background connectivity detection | Detect restored internet connectivity and trigger sync automatically (FR-9.3). | High | 3 | Not Started
T-064 | 11. Offline Operation & Sync Engine | Sync engine | Idempotent upsert sync protocol | Implement UUID-keyed idempotent upserts on the backend to prevent duplicate records (FR-9.4). | High | 5 | Not Started
T-065 | 11. Offline Operation & Sync Engine | Sync engine | Conflict logging (never auto-overwrite local sales) | Ensure server never silently overwrites a completed local sale; log conflicts for review (FR-9.5). | High | 4 | Not Started
T-066 | 11. Offline Operation & Sync Engine | Sync UI feedback | Sync status indicator in UI | Visual badge showing Synced / Pending Sync / Sync Failed per order (FR-9.6). | Medium | 2 | Not Started
T-067 | 12. Reporting & Analytics | Shift reports | X-Report (mid-shift summary) | Generate non-resetting sales summary report on demand (FR-10.1). | Medium | 3 | Not Started
T-068 | 12. Reporting & Analytics | Shift reports | Z-Report (end-of-day summary) | Generate and finalize end-of-day report that resets daily counters (FR-10.2). | High | 3 | Not Started
T-069 | 12. Reporting & Analytics | Sales analytics | Filterable sales report (date/type/method/staff) | Report screen with filters and export, sourced from server when online (FR-10.3, FR-10.6). | Medium | 4 | Not Started
T-070 | 12. Reporting & Analytics | Sales analytics | Best/worst-selling items report | Aggregate query and chart for top/bottom menu items over a period (FR-10.4). | Low | 3 | Not Started
T-071 | 12. Reporting & Analytics | Loss prevention reporting | Voided/discounted transactions report | Separate report surfacing all voids and discounts for review (FR-10.5). | Medium | 2 | Not Started
T-072 | 13. Testing & QA | Unit testing | Unit tests for order/payment/tax logic | Cover core business logic (totals, tax, discounts, stock deduction) with unit tests. | High | 5 | Not Started
T-073 | 13. Testing & QA | Integration testing | End-to-end order flow test (offline scenario) | Simulate full offline order lifecycle: create -> kitchen -> pay -> print -> reconnect -> sync. | High | 5 | Not Started
T-074 | 13. Testing & QA | Integration testing | Sync conflict scenario testing | Test simultaneous edits/duplicate submissions to confirm idempotent sync behavior. | High | 4 | Not Started
T-075 | 13. Testing & QA | Hardware testing | Printer failure/retry testing | Disconnect printer mid-transaction to confirm order completion is not blocked. | Medium | 2 | Not Started
T-076 | 13. Testing & QA | UAT | User acceptance testing with restaurant staff | Walkthrough with actual cashier/waiter/kitchen staff to validate usability (NFR-4.2). | Medium | 4 | Not Started
T-077 | 14. Deployment & Packaging | Desktop packaging | Build signed Windows installer via Tauri | Configure Tauri bundler for Windows .msi/.exe installer output. | High | 3 | Not Started
T-078 | 14. Deployment & Packaging | Backend deployment | Deploy Node/Express/PostgreSQL backend to VPS | Set up production server, environment config, and database backups. | High | 4 | Not Started
T-079 | 14. Deployment & Packaging | Backend deployment | Configure HTTPS/TLS for API and WebSocket | Set up SSL certificates and secure Socket.IO connection (NFR-3.2). | High | 2 | Not Started
T-080 | 14. Deployment & Packaging | Go-live | On-site installation and staff training | Install on restaurant hardware, connect printer, run staff training session. | Medium | 4 | Not Started
T-081 | 14. Deployment & Packaging | Go-live | Post-launch monitoring and hotfix window | Monitor first week of live usage for sync issues, printer errors, and bugs. | Medium | 4 | Not Started

## Summary
Phase | Task Count | Total Est. Hours
1. Project Setup & Environment | 8 | 18
2. Database & Schema Design | 6 | 20
3. Authentication & User Management | 7 | 23
4. Menu Management | 7 | 26
5. Order Management | 8 | 29
6. Table & Floor Management | 4 | 14
7. Kitchen Display System (KDS) | 5 | 17
8. Payment Processing | 6 | 20
9. Inventory Management | 5 | 15
10. Receipt & Printing | 5 | 16
11. Offline Operation & Sync Engine | 5 | 19
12. Reporting & Analytics | 5 | 15
13. Testing & QA | 5 | 20
14. Deployment & Packaging | 5 | 17
TOTAL | 81 | 269